## Sheet1
Task ID | Task Name | Start Date | End Date | Duration
T1 | Requirement gathering (functional + non-functional) | 2025-09-01 | 2025-09-03 | 2
T2 | Stakeholder analysis | 2025-09-04 | 2025-09-05 | 1
T3 | UML Use Case Diagram | 2025-09-06 | 2025-09-07 | 1
T4 | UML Class, Sequence, Activity Diagrams | 2025-09-09 | 2025-09-11 | 2
T5 | Product backlog creation | 2025-09-12 | 2025-09-13 | 1
T6 | Sprint planning (tasks + story points) | 2025-09-15 | 2025-09-16 | 1
T7 | Task assignment in Trello | 2025-09-17 | 2025-09-18 | 1
T8 | Test case preparation (unit, integration, system, UAT) | 2025-09-19 | 2025-09-21 | 2
T9 | GitHub repo updates (requirements, design, test cases) | 2025-09-23 | 2025-09-24 | 1
T10 | Maintainance & Review | 2025-09-25 | 2025-09-27 | 2
45899
45927